## Estimates
S.No | Category | Considerations | Percentage (%) | Min (hrs) | Max (hrs)
1 | Development | Mentioned in the Development tab | 75 | 25 | 36
2 | Testing | This includes end to end testing | 22 | 7.48 | 10.56
3 | Design and Documentation | User manual, Testing document, Tech Design document | 0 | 0 | 0
4 | Deployment | Deployment in orgs post development in shint, bfldev, UAT and Prod. | 0 | 0 | 0
5 | Post Go Live Support | Support would be provided for 2 days post go live | 3 | 1.02 | 1.44
Total |  |  | 100 | 33.3333 | 48
|  | Final Total (Round Up) |  | 34 | 48
|  | Total Weeks (Tentative Schedule) |  | 1 | 2
NOTE : We need to check how to send emails to user in their respective time zone
195

## Development
Approach Details
Features No. | Features | Assumption Details | Category (Configuration/Development) | Complexity | Estimation Consideration | Min (hrs) | Max (hrs) | Open Questions
1 | UI Change for the User detial page |  | Development | Medium |  | 3 | 6
2 | Validation to check only single open survey is open for a user |  | Development | Medium |  | 4 | 6
3 | Handling Prefilled data for User details from email as a source for the end user. |  | Development | Medium |  | 2 | 4
4 | Upadate in the logic to overwrite the if there is a partail filled survey for the user |  | Development | Medium |  | 16 | 20
Sub Total | [5 empty] | 25 | 36
Buffer | [5 empty] | 0 | 0
Total | [5 empty] | 25 | 36
5 | Journey Implementation |  |  |  |  | 40 | 56

## High Level Approach
Phase 1: Survey Response creation & overwrite strategy (data integrity) Goal Ensure data consistency by maintaining one open survey response per user, while allowing users to revisit and update their answers. Core Design Principle When a user revisits the survey, reuse the existing open Survey Response and override related answers instead of creating duplicates. High-Level Flow (Phase 1) User accesses survey (Email / Store) System checks for an existing open Survey Response If found → reuse it If not found → create a new Survey Response On Submit: Existing answers for the response are replaced with the new response No duplicate Survey Response is created.

## Scope Of Implementation
In Scope | Out Of Scope
In- Scope: | Out- Scope:
Note-: