## Estimates
S.No | Category | Considerations | Percentage (%) | Min (hrs) | Max (hrs)
1 | Development | Mentioned in the Development tab | 75 | 47 | 68
2 | Testing | This includes end to end testing | 20 | 12.6 | 18.2
3 | Design and Documentation | User manual, Testing document, Tech Design document | 0 | 0 | 0
4 | Deployment | Deployment in orgs post development in shint, bfldev, UAT and Prod. | 3 | 1.89 | 2.73
5 | Post Go Live Support | Support would be provided for 2 days post go live | 2 | 1.26 | 1.82
Total |  |  | 100 | 62.6667 | 90.6667
|  | Final Total (Round Up) |  | 63 | 91
|  | Total Weeks (Tentative Schedule) |  | 2 | 3
NOTE : We need to check how to send emails to user in their respective time zone
195

## Development
Approach Details
Features No. | Features | Assumption Details | Category (Configuration/Development) | Complexity | Estimation Consideration | Min (hrs) | Max (hrs) | Open Questions
1 | UI Change for the User detial page |  | Development | Medium |  | 3 | 6
2 | Validation to check only single open survey is open for a user |  | Development | Medium |  | 4 | 6
3 | Handleing pre-filled data for partail submession from end user |  | Development | Medium |  | 40 | 56
Sub Total | [5 empty] | 47 | 68
Buffer | [5 empty] | 0 | 0
Total | [5 empty] | 47 | 68
5 | Journey Implementation |  |  |  |  | 40 | 56

## High Level Approach
Phase 2 – Prefill Strategy (User Experience Optimization) Goal Reduce user effort by pre-filling previously saved answers when the user revisits the survey. Core Design Principle If an open Survey Response exists, preload all related answers into the UI. High-Level Flow (Phase 2) User accesses survey System fetches existing open Survey Response Related Answers are retrieved UI pre-fills questions with existing answers

## Scope Of Implementation
In Scope | Out Of Scope
In- Scope: | Out- Scope:
Note-: